## Sheet1
Date | Time In | Time out | Descrption | Total Hrs
Tue, Jan 7, 2024 | 7:30 | 17:00 | Briefing at Kuils River workshop. Traveled to Stellenbosch site: leveled & screeded 60m² surface. Traveled to Paardevlei & Kuils River residential sites for scoping and paving assistance. | 9.5
Wed, Jan 8, 2024 | 7:30 | 17:00 | Workshop briefing. Finished paving and grouting at Kuils River residential site (120m²). Assisted with compaction, cleaning, and brick laying. | 9.5
Thu, Jan 9, 2024 | 7:30 | 17:00 | Picked up team. Worked at Stellenbosch site: paving 60m² area. Corrected paving direction. Mixed and applied grout. | 9.5
Fri, Jan 10, 2024 | 7:30 | 17:00 | Vehicle logistics: returned hired plant to RZ-Hire. Worked at Stellenbosch site: excavated trench and backfilling. | 9.5
Mon, Jan 13, 2024 | 7:30 | 17:00 | Worked at Polkadraai site: Levelled aggregate using surveyor's marks. Operated digger loader. Compacted soil. | 9.5
Tue, Jan 14, 2024 | 7:30 | 17:00 | Continued site preparation at Polkadraai. Assisted with setting up for large-scale paving operation. | 9.5
Wed, Jan 15, 2024 | 7:30 | 17:00 | Worked at Polkadraai site: Operated double-drum roller compactor. Compacted base layers for paving. | 9.5
Thu, Jan 16, 2024 | 7:30 | 17:00 | Operated compactor. Attended client meeting with all subcontractors. Assisted team with paving one cube of bricks (~3000 bricks). | 9.5
Fri, Jan 17, 2024 | 7:30 | 17:00 | Worked at Fig Tree Security Estate, Durbanville: Reinstated driveway paving. Purchased materials. Prepared ground, laid bricks, and grouting. | 9.5
Sat, Jan 18, 2024 | 7:30 | 17:00 | Worked at 6 Sontie St, Kuils River: Prepared for circular paving pattern (180m²). Cleared site. Purchased sand. Assisted with setting out. | 9.5
Mon, Jan 20, 2024 | 7:30 | 17:00 | Worked at 6 Sontie St, Kuils River: Purchased materials. Assisted with grouting process. Checked brick alignment. Cleaned site. | 9.5
Tue, Jan 21, 2024 | 7:30 | 17:00 | Worked at 6 Sontie St, Kuils River: Finalized paving. Afternoon: Traveled to Stikland for Isotech job: installed aluminum stair nosing. | 9.5
Wed, Jan 22, 2024 | 7:30 | 17:00 | Worked at 5 Olympus Dr, Kraaifontein: Construction of garage entrance header with lintels. Built double-skinned brick courses. | 9.5
Thu, Jan 23, 2024 | 7:30 | 17:00 | Worked at 5 Olympus Dr, Kraaifontein: Constructed internal partitioning and cavity wall. Built sliding door entrance brickwork. | 9.5
Fri, Jan 24, 2024 | 7:30 | 17:00 | Worked at 5 Olympus Dr, Kraaifontein: Calculated brick quantities for project. Removed garage door. Supervised site cleaning and tool packing. | 9.5
Mon, Jan 27, 2024 | 7:30 | 17:00 | Transported teams, supervised curb removal (57m), procured materials, assisted with measurements and deliveries. | 9.5
Tue, Jan 28, 2024 | 7:30 | 17:00 | Supervised team, installed and finished new curbs (57m), mixed cement and ensured alignment. | 9.5
Grand Total |  |  |  | 161.5